NW 39th Avenue:    In an area near the Estates of Coconut Creek along NW 39th Avenue, two (2) traffic calming speed tables are scheduled for installation and construction during the next two weeks;

Broward County - Copans Rd Sidewalk Project

The City was notified by Broward County that the existing WB median 24hr lane closure along Copans Road (one lane only) from about NW 42nd Avenue to NW 36th Avenue, will be extended an additional week thru April 1, 2022.

The median opening at NW 40th is closed to allow for the installation of drainage structures.  The County anticipates that the median’s irrigation issue will be resolved this week and that the contractor can complete their median work within the next week.

Peak hour delays are anticipated along WB Copans Road and residents are encourage to seek alternative routes, if possible.

Broward County - Copans Road at NW 42nd Avenue Mast Arm Upgrade Project

The contactor is mobilizing to the project site this week.  Clearing and grubbing work is scheduled to begin.  The work is scheduled to extend into mid-June 2022.

FDOT - Lyons Road Project

A field walk thru with City Staff to review roadway condition deficiencies vs. the approved FDOT design plans has been scheduled for most of next week (3/28/22);

The pattern pavement crosswalks are continuing to be installed along the corridor;

City Staff requested the median’s concrete curbs within the project work zone be cleaned again and re-inspected in a manner acceptable to City Staff;

A comprehensive project punch list of open items has been revised by City Staff and sent to the CEI team.  A field walk thru with City Staff and Broward County Staff will be forthcoming; and

Project completion is anticipated to be around late April 2022 as the project still remains ahead of schedule and is under budget.